## Summary
*biological, microenvironment, small molecules
Data Release 1 |  | Data Generation | [10 empty] | Data release schedule
Project | Short Descriptive Label | perturbagens: external* |  |  | perturbagens: diseases | perturbagens: genetic | # bio reps | cell types |  | cellular phenotypes | targets/ readouts monitored | Total # of Measurements | Level 1 | Level 2 | Level 3 | Level 4
|  | count | doses | time points | count | count |  | cell lines | iPS, differentiated
Cardiotoxicity Signatures | RNASeq | 30 | 1 | 1 |  |  | 3 | 3 |  |  |  |  | 2015-04-30 | 2015-04-30 | 2015-04-30 | 2015-04-30
| Proteomics | 10 | 1 | 1 |  |  | 3 | 3
| Western blots/PCR (validation assays) | 15 | 1 | 1 |  |  | 3 | 3
Data Release 2
Cardiotoxicity Signatures | RNASeq | 30 | 1 | 1 |  |  | 3 | 1 | 2 |  |  |  | 2015-07-31 | 2015-07-31 | 2015-07-31 | 2015-07-31
| Proteomics | 10 | 1 | 1 |  |  | 3 | 1 | 2
| Western blots/PCR (validation assays) | 15 | 1 | 1 |  |  | 3 | 1 | 2
Data Release 3
Cardiotoxicity Signatures | RNASeq | 30 | 1 | 1 |  |  | 3 |  | 2 |  |  |  | 2015-10-31 | 2015-10-31 | 2015-10-31 | 2015-10-31
| Proteomics | 10 | 1 | 1 |  |  | 3 |  | 2
| Western blots/PCR (validation assays) | 15 | 1 | 1 |  |  | 3 |  | 2
Cardiomyocyte "Efficacy/Toxicity Ratio" Joint project- Collaborators: ISMMS, UCI, HMS, Broad/Golub, Broad/Jaffe, OHSU & DCIC* | RNASeq | 6 | 6 | 1 |  |  | 3 | 4 |  |  |  |  | 2015-10-31 | 2015-10-31 | 2015-10-31 | 2015-10-31
| Proteomics | 6 | 6 | 1 |  |  | 3 | 4
| Western blots/PCR (validation assays) | 15 | 6 | 1 |  |  | 3 | 4
*More information about joint projects can be found on x spreadsheet
Data Release 4
Cardiotoxicity Signatures | RNASeq | 30 | 1 | 1 |  |  | 3 |  | 2 |  |  |  | 2016-01-31 | 2016-01-31 | 2016-01-31 | 2016-01-31
| Proteomics | 10 | 1 | 1 |  |  | 3 |  | 2
| western blots | 2--4 | 1 | 1 |  |  | 3 |  | 2

## Perturbagens
Perturbagens
Afatinib
Axitinib
Bosutinib
Cabozantinib
Ceritinib
Crizotinib
Dabrafenib
Dasatinib
Erlotinib
Gefitinib
Imatinib
Lapatinib
Nilotinib
Pazopanib
Ponatinib
Regorafenib
Ruxolitinib
Sorafenib
Sunitinib
Tofacitinib
Trametinib
Vandetanib
Vemurafenib
Trastuzumab
Trastuzumab + Ursodeoxycholic acid
Trastuzumab + Loperamide
Trastuzumab + Domperidone
Sunitinib + Ursodeoxycholic acid
Sunitinib + Domperidone
Sunitinib + Loparemide
Sunitinib + Prednisolone
Sorafenib + Ursodeoxycholic acid
Sorafenib + Entecavir
Sorafenib + Diethylpropion
Sorafenib + Olmesartan
Sorefenib + Diclofenac
Dasatinib + Cytarabine
Erlotinib + Cefuroxime
Imatinib + Cyclosporine
Ursodeoxycholic acid
Loperamide
Domperidone
Prednisolone
Entecavir
Diethylpropion
Olmesartan
Diclofenac
Cytarabine
Cefuroxime
Cyclosporine

## Data generation timeline
Drug Treatment and Signature Generation Experiments
Cell line | Perturbagens | Raw data, release date | Processed data, release date | Experimental conditions | Biological Replicates | Validation assays
Promocell myoyctes, Line 1 | Kinase inhibitors associated with cardiotoxicity with and without mitigating drugs as determined by analysis of FAERS. The list is provided below. Total number of drugs that will be tested in 2015 will depend on the cost mRNA-Seq. At current prices we will test 30 purtabagens with RNAseq. 10 of these perturbagens will be examined using proteomics | 2015-04-30 | 2015-04-30 | Cells treated with drug or drugs) for 48hrs at a single concentration corresponding to total plasma concentrations in humans, harvest cells, extract mRNA and protein for mRNA –Seq and protein measurements. | 3 | Differential expression levels of 10-15 transcripts will be validated on every 10th sample using PCR, and 2-4 proteins using Western blots.
Promocell myoyctes, Line 2
Promocell myoyctes, Line 3
Promocell myoyctes, Line 4 |  | 2015-07-31 | 2015-07-31 |  | 3
Myocytes derived from NeuroLINCS iPSCs, Line 1
Myocytes derived from NeuroLINCS iPSCs, Line 2
Mount Sinai iPSC-derived myocytes, Line 1 |  | 2015-10-31 | 2015-10-31 |  | 3
Mount Sinai iPSC-derived myocytes, Line 2
Mount Sinai iPSC-derived myocytes, Line 3 |  | 2016-01-31 | 2016-01-31 |  | 3
Mount Sinai iPSC-derived myocytes, Line 4
Healthy Subject iPSC generation
iPSCS from 6 healthy subjects | none | NA | 2015-07-31 | NA | 6-10 clones from each subject | Pluripotency of each clone will be experimentally tested
iPSCS from 24 | none | NA | 2016-01-31 | NA | 6-10 clones from each subject | Pluripotency of each clone will be experimentally tested
healthy subjects
Notes
Generation of iPSC-derived Myocytes:We will generate iPSC-derived cardiomyocyte lines from 30 healthy volunteers at Mount Sinai. Individual subjects will be clinically screened for health status in the Mount Sinai CRC. After verification of healthy status we will collect skin biopsies, isolate fibroblasts and program these cells into iPSCs. We plan to have at least 4 Mount Sinai iPSC lines generated by the end of year one (June 2015). In the latter half of 2015 these will be differentiated into myocytes, tested with perturbagens, and assayed with RNAseq and proteomics.
Perturbagen :All perturbagens will be FDA approved drugs. List is provide on Page 3
Compliance Level: We expect that data will be 100% compliant with existing metadata standards. In addition, we also anticipate that metadata standards will evolve to accommodate additional metadata thatwill be generated in our experiments and computation.
Types of Data to be released: 1) Statistically ranked lists of DEGs and DEPs , 2) Networks as undirected graphs , 3) Dynamical models of subnetworks related to drug action. # 3 will be released after 31 Jul 2015 nQA/QC and metadata for #3 will be specified by April 30 , 2015
Data Release: At the time of processed data release, all metadata, experimental and computational will also be released. Lists of differentially expressed genes and subnetworks they belong to will be released as processed. mRNA-Seq data will be compliant with TCGA standards
Validation Assays may not be fully completed before processed data is released.

## Cardiomyocyte Dense Cube
LINCS Cardiomyocyte Dense Cube – Efficacy/toxicity ratio
Cell line | Perturbagens | Raw data, release date | Processed data, release date | Experimental conditions | Technical Replicates | Biological Replicates | Validation assays
Promocell myoyctes, Line 1 | 6 Kinase inhibitors associated with cardiotoxicity will be tested at 6 concentrations in each cell line | 2015-10-30 | 2015-10-30 | Cells treated with drug or drugs) for 48hrs at indicated concentrations, harvest cells, extract mRNA , | 3 | 3 | Differential expression levels of 10-15 transcripts will be validated on every 10th sample using PCR, and 2-4 proteins using Western blots.
for L-1000 measurements and protein extraction
Promocell myoyctes, Line 2 |  |  |  | for L-100 measurements. | 3 | 3
Myocytes derived from NeuroLINCS iPSCs, Line 1 |  |  |  |  | 3 | 3
Myocytes derived from NeuroLINCS iPSCs, Line 2 |  |  |  |  | 3 | 3 |  | are they planning on doing this?
Cancer Cell lines 1-4 HMS LINCS Center |  | 2015-10-30 |  |  | 3 for each cell line | 3 for each cell line |  | are these six kinase inhibitors part of the original list
Notes
Cell Lines : Cancer Cell lines will be selected by HMS group in consultation with the Mount Sinai group
Perturbagen :All purtabugens will be FDA approved drugs. Single drugs will be tested at 6 concentrations
Compliance Level: We expect that data will be 100% compliant with existing metadata standards. In addition, we also anticipate that metadata standards will evolve to accommodate additional metadata thatwill be generated in our experiments and computation.
Types of Processed data to be released: 1) Statistically ranked lists of DEGs and DEPs , 2) Networks as undirected graphs ,
Data Release: At the time of processed data release, all metadata, experimental and computational will also be released. Lists of differentially expressed genes and subnetworks they belong to will be released as processed. mRNA-Seq data will be compliant with TCGA standards
Validation Assays may not be fully completed before processed data is released.
A preliminary description of an additional collaborative Project is described on page 9