## HMS-Proposed Milestones Dec2014
Proposed NeuroLINCS Dataset Milestones for September 2014-December 2015 (submitted 12-23-14)
Note 1: See attached document for NeuroLINCS QA/QC information and description of validation assays.
Note 2: All NeuroLINCS data will be released in formats compliant with LINCS metadata standards.
change to phenotypes
Datasets | Assay information | Cells | Perturbations |  |  |  | Timepoints | Targets/Readouts monitored | Data--estimated release dates |  |  | Comments/relevant urls (for released datasets)
|  | cell lines |  |  | small molecules | small molecule doses | timepoints (hours)
iMN toxicity as determined by RM | Imaging assay--monitoring cell survival in control, ALS, and SMA iMNs. iMNs will be transfected with a fluorescence reporter and imaged daily for 10 days. Images will be run through a custom analysis software package that tracks individual cells over time. The time of death (if it occurs) for each neuron will be determined. Neurite arborization will be determined using custom software analysis on these images. . | CS00iCTR-n2 |  |  |  |  | ~24 hours | cell fluorescence | Y1 Q3 | Y1 Q4 | Y2 Q1
|  | CS14iCTR-n6 |  |  |  |  | ~48 hours | survival time | Y1 Q3 | Y1 Q4 | Y2 Q1
|  | CS83iCTR-33n1 |  |  |  |  | ~72 hours | morphology | Y1 Q3 | Y1 Q4 | Y2 Q1
|  | CS25iCTR-18n2 |  |  |  |  | ~96 hours
|  | CS28iALS-n2A |  |  |  |  | ~120 hours
|  | CS29iALS-n1N |  |  |  |  | ~144 hours
CS30iALS-n1A
CS52iALS-n6A
CS32iSMA-n3
CS13iSMA-n1
83iSMA-n5
CS77iSMA-n5
|  | cell lines |  |  | small molecules | small molecule doses μM | timepoints (hours)
iMN glutamate toxicity- Excitotoxicity | iPSN Sensitivity to Glutamate-induced Toxicity To test iPSN sensitivity to glutamate-induced excitotoxicity, control and ALS/SMA iPSNs will be treated with various concentrations of L-glutamate (1, 3, 10, 30, 100 μM) for 2 – 8 hr in NDM, all concentrations for each experiment will be performed in triplicate. At the appropriate time point, cells will be incubated with 1 μM propidium iodide and 1 μM calcein AM for 30 min to visualize dead and live cells, respectively. Five to ten fields of view will then be imaged for each treatment using excitation/emission filters of 535/617 nm and 495/515 nm for propidium iodide and calcein AM, respectively. The number of propidium iodide positive and calcein AM iPSNs will be quantified using Image J over 3 separate experiments. | CS00iCTR-n2 |  |  | Glutamate | 1 | 2 hours | cell fluoresence after propidium iodide | Y1 Q3 | Y1 Q4 | Y2 Q1
|  | CS14iCTR-n6 |  |  |  | 3 | 4 hours | # cells with PI uptake | Y1 Q3 | Y1 Q4 | Y2 Q1
|  | CS83iCTR-33n1 |  |  |  | 10 | 6 hours |  | Y1 Q3 | Y1 Q4 | Y2 Q1
|  | CS25iCTR-18n2 |  |  |  | 30 | 8 hours
|  | CS28iALS-n2A |  |  |  | 100
CS29iALS-n1N
CS30iALS-n1A
CS52iALS-n6A
CS32iSMA-n3
CS13iSMA-n1
83iSMA-n5
CS77iSMA-n5
|  | cell lines |  |  | small molecules | small molecule doses μM | timepoints (hours)
iMN Tunicamycin Toxicity: ER Stress | Sensitivity to tunicamycin/ER Stress. iPS neurons will be differentiated in 24 well plates for 39 days before treatment with increasing tunicamycin concentrations (0, 0.1, 0.3, 0.6, 1.0, or 3.0 μM). After 24 h of incubation with tunicamycin, 0.5 μM of propidium iodide (PI) will be added to each well and incubated for 30 minutes. The PI signal will be imaged. For each treatment and dose, ≥ 10 images were taken per experiment, and the number of iPS neurons exhibiting PI uptake will be quantified using the “analyze particle” function of the Image J software (NIH). | CS00iCTR-n2 |  |  | tunicamycin | 0 | 24 hours | cell fluoresence after propidium iodide | Y1 Q3 | Y1 Q4 | Y2 Q1
|  | CS14iCTR-n6 |  |  |  | 0.1 |  | # cel with PI uptake | Y1 Q3 | Y1 Q4 | Y2 Q1
|  | CS83iCTR-33n1 |  |  |  | 0.3 |  | 10 images per experiment | Y1 Q3 | Y1 Q4 | Y2 Q1
|  | CS25iCTR-18n2 |  |  |  | 0.6 |  | “analyze particle” function of the Image J software | Y1 Q3 | Y1 Q4 | Y2 Q1
|  | CS28iALS-n2A |  |  |  | 1
|  | CS29iALS-n1N |  |  |  | 3
|  | CS30iALS-n1A | [5 empty] | ex. 1 target, 1 phenotype
CS52iALS-n6A
CS32iSMA-n3
CS13iSMA-n1
83iSMA-n5
CS77iSMA-n5
Baseline RNAseq for control and diseased iPSC lines | Baseline gene expression dataset for QC and pipeline development -- 11 total control iPSC cell lines 3 in triplicate and 1 in duplicate and 28 diseased iPSC, 4 ALS and 4 SMA with replicates and with no additional perturbagen. Determine cell line variability and assay reproducibility. RNAseq QC statistics and expression correlation statistics will guide the development of QC statndards and appropriate analysis pipeline. |  |  |  | N/A |  |  | Read counts | Y1 Q3 | Y1 Q4 |  | FastQC, RSeqQC, RNA-SeQC, GENE-E, IGV
[8 empty] | FPKM | Y1 Q3 | Y1 Q4 |  | TuxedoSuite, DESeq, EdgeR
[8 empty] | Statistically significant DEGs | Y1 Q3 | Y1 Q4
RNAseq for control and diseased iMNs | Baseline gene expression dataset for iMN and diseased state signature -- 4 control, 4 ALS, and 4 SMA iPSC-derived iMN with replicates and with no additional perturbagen. Generate gene expression signatures and analyze disease/control contrast for statistically significant differentially expressed genes. Generate disease signatures for future systems analysis: pathway, network, and category enrichment analysis, as well as for integration with other omics and machine learning analyses. |  |  |  | N/A |  |  | Read counts |  | Y1 Q4 | Y2 Q1 | QC and RNAseq analysis tools determined from baseline pilot study above.
[8 empty] | FPKM |  | Y1 Q4 | Y2 Q1
[8 empty] | Statistically significant DEGs |  | Y1 Q4 | Y2 Q1
RNAseq for control and diseased iMNs plus perturbations | Gene expression dataset for iMN and disease signature reponse to perturbagens -- 4 control, 4 ALS, and 4 SMA iPSC-derived iMN with replicates plus additional perturbagen. Generate gene expression signatures and for both disease and control and analyze perturb/disease & perturb/control contrasts for statistically significant differentially expressed genes. Using a GLM setup multi-factor design matrix to analyze disease vs control with each perturbagen as an additional factor. Generate signatures for future systems analysis: pathway, network, and category enrichment analysis, as well as for integration with other omics and machine learning analyses. |  |  |  | ASO |  |  | Read counts |  |  | Y2 Q1 | QC and RNAseq analysis tools determined from baseline pilot study above.
[5 empty] | TBD |  |  | FPKM |  |  | Y2 Q1
[8 empty] | Statistically significant DEGs |  |  | Y2 Q1
Proteomic QC and database comparison |  | cell lines |  | Dose
https://docs.google.com/spreadsheets/d/1PyM4Gy8Wj8iKV_dZKwuPFLECj-8Cj3IMloDrEnz4Ivw/edit#gid=1971812578
QC and SOP development for proteomic analysis iPSC to motor neuron differentiation | a) MS analysis on the QE and or Triple TOF MS instrument of trypsin digested iPSC dervied from 4 control, 4 ALS and 4 SMA lines for 3 different wells at multiple cell passages. | CS00iCTR-n2 | multiple wells | multple passages |  |  |  |  | Y1 Q3 | Y1 Q4
a) iPSC |  | CS14iCTR-n6 | multiple wells | multple passages | [7 empty] | https://docs.google.com/spreadsheets/d/1v7mDOVG7DgHLRFdgM9BP3Zj1ywCkofFNbDBJktjiRwY/edit#gid=2003204207
|  | CS83iCTR-33n1 | multiple wells | multple passages
|  | CS25iCTR-18n2 | multiple wells | multple passages | [7 empty] | https://docs.google.com/spreadsheets/d/1-xXPwv5H_DqgIcor1k4CWyQU4dv0piyFhzuwmnGUqwg/edit#gid=446440341
|  | CS28iALS-n2A | multiple wells | multple passages
|  | CS29iALS-n1N | multiple wells | multple passages
|  | CS30iALS-n1A | multiple wells | multple passages
|  | CS52iALS-n6A | multiple wells | multple passages
|  | CS32iSMA-n3 | multiple wells | multple passages
|  | CS13iSMA-n1 | multiple wells | multple passages
|  | 83iSMA-n5 | multiple wells | multple passages
|  | CS77iSMA-n5 | multiple wells | multple passages
SWATH global cellular protein quantification | Assay Information | cell lines | subfractions
Compare iPSC and mature differentitated neurons | Build MS SWATH data library: using the QE and 6600 MS instrument analyzing either fractionated individuals and pools of iPSC dervied from 4 controls and SMA and ALS lines into soluble, insoluble and acid soluble. | [10 empty] | build composite SWATH libary
| A) build SWATH Library | control 83i-IPSC | soluble, insoluble and acid extraction | [5 empty] | Y1 Q3 | Y1 Q4 | Y2Q1 | build composite SWATH libary
|  | Control 49i-IPSC | soluble, insoluble and acid extraction | [8 empty] | build composite SWATH libary
|  | SMA 84i-IPSC | soluble, insoluble and acid extraction | [8 empty] | build composite SWATH libary
|  | pool control-IPSC | soluble, insoluble and acid extraction | [8 empty] | build composite SWATH libary
|  | pool of ALS-IPSC | soluble, insoluble and acid extraction | [8 empty] | build composite SWATH libary
|  | pool of SMA-IPSC | soluble, insoluble and acid extraction | [8 empty] | build composite SWATH libary
|  | pool control-mature motor neurons | soluble, insoluble and acid extraction | [6 empty] | Y1Q4 | Y2Q1 | build composite SWATH libary
|  | pool of ALS-mature motor neurons | soluble, insoluble and acid extraction | [8 empty] | build composite SWATH libary
|  | pool of SMA-mature motor neurons | soluble, insoluble and acid extraction | [8 empty] | build composite SWATH libary
| B) Run individual iPSC cells | CS00iCTR-n2-IPSC | cell homogenate
|  | CS14iCTR-n6-IPSC | cell homogenate | [5 empty] | Y1Q3 | Y1Q4
|  | CS83iCTR-33n1-IPSC | cell homogenate
|  | CS25iCTR-18n2-IPSC | cell homogenate
|  | CS28iALS-n2A-IPSC | cell homogenate
|  | CS29iALS-n1N-IPSC | cell homogenate
|  | CS30iALS-n1A-IPSC | cell homogenate
|  | CS52iALS-n6A-IPSC | cell homogenate
|  | CS32iSMA-n3-IPSC | cell homogenate
|  | CS13iSMA-n1-IPSC | cell homogenate
|  | 83iSMA-n5-IPSC | cell homogenate
|  | CS77iSMA-n5-IPSC | cell homogenate
| C) Run individual mature motor neurons | CS00iCTR-n2-mature motor neurons | cell homogenate | [6 empty] | Y1Q4 | Y2 Q1
|  | CS14iCTR-n6-mature motor neurons | cell homogenate
|  | CS83iCTR-33n1-mature motor neurons | cell homogenate
|  | CS25iCTR-18n2-mature motor neurons | cell homogenate
|  | CS28iALS-n2A-mature motor neurons | cell homogenate
|  | CS29iALS-n1N-mature motor neurons | cell homogenate
|  | CS30iALS-n1A-mature motor neurons | cell homogenate
|  | CS52iALS-n6A-mature motor neurons | cell homogenate
|  | CS32iSMA-n3-mature motor neurons | cell homogenate
|  | CS13iSMA-n1-mature motor neurons | cell homogenate
|  | 83iSMA--mature motor neurons | cell homogenate
|  | CS77iSMA-n5-mature motor neuron | cell homogenate
Phosphorylation state |  | cell lines | subfractions
Compare iPSC, neural rosettes and differentated neurons | Build MS SWATH data library: using the 6600 MS instrument analyzing either fractionated individuals and pools of iPSC dervied from 4 controls and SMA and ALS lines into soluble, insoluble and acid soluble enriched for phosphorylation. | [7 empty] | Y1Q3 | Y1Q4 | Y2 Q1
A) build SWATH Library
|  | pool control iPSC-phosphorylation enriched | soluble, insoluble and acid extraction -phosphorylation enriched | [8 empty] | build composite SWATH libary
|  | pool of ALS iPSC--phosphorylation enriched | soluble, insoluble and acid extraction -phosphorylation enriched | [8 empty] | build composite SWATH libary
|  | pool of SMA iPSC--phosphorylation enriched | soluble, insoluble and acid extraction -phosphorylation enriched | [8 empty] | build composite SWATH libary
|  | pool control -mature motor neurons-phosphorylation enriched | soluble, insoluble and acid extraction -phosphorylation enriched | [8 empty] | build composite SWATH libary
|  | pool of ALS -mature motor neurons--phosphorylation enriched | soluble, insoluble and acid extraction -phosphorylation enriched | [8 empty] | build composite SWATH libary
|  | pool of SMA -mature motor neurons--phosphorylation enriched | soluble, insoluble and acid extraction -phosphorylation enriched | [8 empty] | build composite SWATH libary
[10 empty] | Y1Q4 | Y2 Q1
| B) Run individual iPSC cells | CS00iCTR-n2-phosphorylation enriched | cell homogenate-phosphorylation enriched
|  | CS14iCTR-n6-phosphorylation enriched | cell homogenate-phosphorylation enriched
|  | CS83iCTR-33n1-phosphorylation enriched | cell homogenate-phosphorylation enriched
|  | CS25iCTR-18n2-phosphorylation enriched | cell homogenate-phosphorylation enriched
|  | CS28iALS-n2A-IPSC-phosphorylation enriched | cell homogenate-phosphorylation enriched
|  | CS29iALS-n1N-IPSC-phosphorylation enriched | cell homogenate-phosphorylation enriched
|  | CS30iALS-n1A-IPSC-phosphorylation enriched | cell homogenate-phosphorylation enriched
|  | CS52iALS-n6A-IPSC-phosphorylation enriched | cell homogenate-phosphorylation enriched
|  | CS32iSMA-IPSC-n3-phosphorylation enriched | cell homogenate-phosphorylation enriched
|  | CS13iSMA-n1IPSC--phosphorylation enriched | cell homogenate-phosphorylation enriched
|  | 83iSMA-n5-IPSC-phosphorylation enriched | cell homogenate-phosphorylation enriched
| C) Run individual mature motor neurons | 83iCTR iPSC-mature motor neurons-phosphorylation enriched | cell homogenate-phosphorylation enriched
|  | 25iCTR iPSC-mature motor neurons-phosphorylation enriched | cell homogenate-phosphorylation enriched | [6 empty] | Y1Q4 | Y2 Q1
|  | 14iCTR iPSC-mature motor neurons-phosphorylation enriched | cell homogenate-phosphorylation enriched
|  | 00iCTR iPSC-mature motor neurons-phosphorylation enriched | cell homogenate-phosphorylation enriched
|  | CS28iALS-n2A-mature motor neurons-phosphorylation enriched | cell homogenate-phosphorylation enriched
|  | CS29iALS-n1N-mature motor neurons-phosphorylation enriched | cell homogenate-phosphorylation enriched
|  | CS30iALS-n1A-mature motor neurons-phosphorylation enriched | cell homogenate-phosphorylation enriched
|  | CS52iALS-n6A-mature motor neurons-phosphorylation enriched | cell homogenate-phosphorylation enriched
|  | CS32iSMA-n3-mature motor neurons-phosphorylation enriched | cell homogenate-phosphorylation enriched
|  | CS13iSMA-n1-mature motor neurons-phosphorylation enriched | cell homogenate-phosphorylation enriched
|  | 83iSMA--mature motor neurons-phosphorylation enriched | cell homogenate-phosphorylation enriched
|  | CS77iSMA-n5-mature motor neuron-phosphorylation enriched | cell homogenate-phosphorylation enriched
Next stage with perturbations
various perturbations on IPSC and potentailly neurons | A) Run individual iPSC cells with stimulation A-N | CS00iCTR-n2 | cell homogenate | [7 empty] | Y2Q1
analyze total protein and phosphorylation initally |  | CS14iCTR-n6 | cell homogenate
|  | CS83iCTR-33n1 | cell homogenate
|  | CS25iCTR-18n2 | cell homogenate
|  | CS28iALS-n2A | cell homogenate
|  | CS29iALS-n1N | cell homogenate
|  | CS30iALS-n1A | cell homogenate
|  | CS52iALS-n6A | cell homogenate
|  | CS32iSMA-n3 | cell homogenate
|  | CS13iSMA-n1 | cell homogenate
|  | 83iSMA-n5 | cell homogenate
| B) Run individual mature motor neurons with stimulation A-N | CS00iCTR-n2-mature motor neurons | cell homogenate
|  | CS14iCTR-n6-mature motor neurons | cell homogenate
|  | CS83iCTR-33n1-mature motor neurons | cell homogenate
|  | CS25iCTR-18n2-mature motor neurons | cell homogenate
|  | CS28iALS-n2A-mature motor neurons | cell homogenate
|  | CS29iALS-n1N-mature motor neurons | cell homogenate
|  | CS30iALS-n1A-mature motor neurons | cell homogenate
|  | CS52iALS-n6A-mature motor neurons | cell homogenate
|  | CS32iSMA-n3-mature motor neurons | cell homogenate
|  | CS13iSMA-n1-mature motor neurons | cell homogenate
|  | 83iSMA--mature motor neurons | cell homogenate
|  | CS77iSMA-n5-mature motor neuron | cell homogenate
| C) Run individual iPSC cells with stimulation A-N | 83iCTR iPSC--phosphorylation enriched | cell homogenate-phosphorylation enriched
|  | 25iCTR iPSC -phosphorylation enriched | cell homogenate-phosphorylation enriched
|  | 14iCTR iPSC-phosphorylation enriched | cell homogenate-phosphorylation enriched
|  | 00iCTR iPSC-phosphorylation enriched | cell homogenate-phosphorylation enriched
|  | CS28iALS-n2A-IPSC-phosphorylation enriched | cell homogenate-phosphorylation enriched
|  | CS29iALS-n1N-IPSC-phosphorylation enriched | cell homogenate-phosphorylation enriched
|  | CS30iALS-n1A-IPSC-phosphorylation enriched | cell homogenate-phosphorylation enriched
|  | CS52iALS-n6A-IPSC-phosphorylation enriched | cell homogenate-phosphorylation enriched
|  | CS32iSMA-IPSC-n3-phosphorylation enriched | cell homogenate-phosphorylation enriched
|  | CS13iSMA-n1IPSC--phosphorylation enriched | cell homogenate-phosphorylation enriched
|  | 83iSMA-n5-IPSC-phosphorylation enriched | cell homogenate-phosphorylation enriched
| D) Run individual mature motor neurons with stimulation A-N | 83iCTR iPSC-mature motor neurons-phosphorylation enriched | cell homogenate-phosphorylation enriched
|  | 25iCTR iPSC-mature motor neurons-phosphorylation enriched | cell homogenate-phosphorylation enriched
|  | 14iCTR iPSC-mature motor neurons-phosphorylation enriched | cell homogenate-phosphorylation enriched
|  | 00iCTR iPSC-mature motor neurons-phosphorylation enriched | cell homogenate-phosphorylation enriched
|  | CS28iALS-n2A-mature motor neurons-phosphorylation enriched | cell homogenate-phosphorylation enriched
|  | CS29iALS-n1N-mature motor neurons-phosphorylation enriched | cell homogenate-phosphorylation enriched
|  | CS30iALS-n1A-mature motor neurons-phosphorylation enriched | cell homogenate-phosphorylation enriched
|  | CS52iALS-n6A-mature motor neurons-phosphorylation enriched | cell homogenate-phosphorylation enriched
|  | CS32iSMA-n3-mature motor neurons-phosphorylation enriched | cell homogenate-phosphorylation enriched
|  | CS13iSMA-n1-mature motor neurons-phosphorylation enriched | cell homogenate-phosphorylation enriched
|  | 83iSMA--mature motor neurons-phosphorylation enriched | cell homogenate-phosphorylation enriched
|  | CS77iSMA-n5-mature motor neuron-phosphorylation enriched | cell homogenate-phosphorylation enriched
Epigenomics |  | cell lines
General information and metadata links | Transposase-based epigenomic assay to map open chromatin regions and infer regulatory protein binding sites | CS00iCTR-n2
CS14iCTR-n6
CS83iCTR-33n1
CS25iCTR-18n2
CS28iALS-n2A
CS29iALS-n1N
CS30iALS-n1A
CS52iALS-n6A
CS32iSMA-n3
CS13iSMA-n1
83iSMA-n5
CS77iSMA-n5
Baseline ATAC-Seq for control and disease iPSC lines | Baseline ATAC-seq experiments for protocol assay optimization, QC and development of analysis methods -- 4 control, 4 ALS and 4 SMA iPSC cell lines with replicates, without additional perturbagens. Determine optimal conditions for purification of high quality nuclei to preserve chromatin structure and for transposase reaction (number of nuclei, enzyme concentration and incubation time) to avoid over- or under-digestion. Set up analysis pipelines and perform correlation and clustering tests to determine cell line variability and assay reproducibility between either technical or biological replicates and Identify potential problematic samples . |  |  |  | N/A |  |  | Raw Data (fastq) and BAM files (aligned reads) | Y1 Q3 | Y1 Q4 | Y2 Q1 | Bowtie, FastQC
[8 empty] | Genomic coordinates and intensity for each significant peak | Y1 Q3 | Y1 Q4 | Y2 Q1 | MACS, GPS
[8 empty] | Differentially expressed peaks relative to population control | Y1 Q3 | Y1 Q4 | Y2 Q1 | MaNorm
ATAC-Seq for control and disease iMNs | Baseline ATAC-seq experiments for iMN and disease state signatures -- 4 control, 4 ALS, and 4 SMA iPSC-derived iMN lines with replicates without additional perturbagens. Annotate open chromatin regions and map transcription factor binding events in regulatory elements genome-wide. Generate chromatin accessibility signatures for each sample individually by calculating the enrichment of genomic regions relative to a set of control reads from Tn5-treated naked genomic DNA. Detect differential peaks between disease and control state. Generate disease signatures for future systems analysis and integration with other omics by 1) identifying genes mapping near differential peaks and detecting significantly enriched GO terms for these gene lists; 2) performing DNA foorprinting, motif scoring and applying regression methods to infer transcription factors responsible for gene expression signatures. |  |  |  | N/A |  |  | Raw Data (fastq) and BAM files (aligned reads) |  | Y1 Q4 | Y2 Q1 | QC and ATAC-Seq analysis tools determined from baseline pilot study above.
[8 empty] | Genomic coordinates and intensity for each significant peak |  | Y1 Q4 | Y2 Q1
[8 empty] | Differentially expressed peaks relative to population control |  | Y1 Q4 | Y2 Q1
ATAC-Seq for control and disease iMNs plus perturbations | ATAC-seq dataset for iMN and disease signature reponse to perturbagens -- 4 control, 4 ALS, and 4 SMA iPSC-derived iMN lines with replicates plus additional perturbagens. Generate chromatin accessibility signatures for each sample individually by calculating the enrichment of genomic regions relative to a set of control reads from Tn5-treated naked genomic DNA. Analyze perturb/disease & perturb/control datasets to detecte differentially enriched peaks reflecting changes in chromatin structures as a consequence of perturbation. Generate disease signatures for future systems analysis and integration with other omics and machine learning analyses. |  |  |  | ASO |  |  | Raw Data (fastq) and BAM files (aligned reads) |  |  | Y2 Q1 | QC and ATAC-Seq analysis tools determined from baseline pilot study above.
[5 empty] | TBD |  |  | Genomic coordinates and intensity for each significant peak |  |  | Y2 Q1
[8 empty] | Differentially expressed peaks relative to population control |  |  | Y2 Q1
Note on C104: Jennifer Van Eyk: should we replicate this for neurons and roseettes?
Note on C117: Jennifer Van Eyk: should we replicate this for neurons and roseettes?

## Summary
*biological, microenvironment, small molecules
Data Release 1 |  | Data Generation | [10 empty] | Data release schedule
Project | Short Descriptive Label | perturbagens: external* |  |  | perturbagens: diseases | perturbagens: genetic | # bio reps | cell types |  | cellular phenotypes | targets/ readouts monitored | Total # of Measurements | Level 1 | Level 2 | Level 3 | Level 4
|  | count | doses | time points | count | count |  | cell lines | iPS, differentiated
Imaging: Cell death assay and perturbations | iMN toxicity as determined by RM |  |  | 6 | 2 |  | 2 |  | 12 | 3 |  |  | Y1 Q3
| iMN glutamate toxicity- Excitotoxicity | 1 | 5 | 4 | 2 |  | 2 |  | 12 | 2 |  |  | Y1 Q3
| iMN Tunicamycin Toxicity: ER Stress | 1 | 6 | 1 | 2 |  | 2 |  | 12 | 2 | 1 |  | Y1 Q3
Transcriptomics | RNAseq for control and diseased iPSC lines, diseased iMNs, with perturbations | TBD |  |  | 2 |  |  |  | 12 |  |  |  | Y1 Q3
Quantitative discovery proteomics (SWATH) | Based on SWATH library, compare iPSC and mature differentitated neurons, phosphorylation state, and add perturbations | 2 |  |  | 2 |  |  |  | 12,12* |  |  |  | Y1 Q3
Epigenomics | ATAC-Seq for control and disease iPSC lines, iMNs, add perturbations | TBD |  |  | 2 |  | 3 |  | 12 |  |  |  | Y1 Q3
*12 iPS, 12 mature motor neurons
Data Release 2
Imaging: Cell death assay and perturbations | iMN toxicity as determined by RM |  |  | 6 | 2 |  | 2 |  | 12 | 3 |  |  |  | Y1 Q4
| iMN glutamate toxicity- Excitotoxicity | 1 | 5 | 4 | 2 |  | 2 |  | 12 | 2 |  |  |  | Y1 Q4
| iMN Tunicamycin Toxicity: ER Stress | 1 | 6 | 1 | 2 |  | 2 |  | 12 | 2 | 1 |  |  | Y1 Q4
Transcriptomics | RNAseq for control and diseased iPSC lines, diseased iMNs, with perturbations | TBD |  |  | 2 |  |  |  | 12 |  |  |  |  | Y1 Q4
Quantitative discovery proteomics (SWATH) | Based on SWATH library, compare iPSC and mature differentitated neurons, phosphorylation state, and add perturbations | 2 |  |  | 2 |  |  |  | 12,12* |  |  |  |  | Y1 Q4
Epigenomics | ATAC-Seq for control and disease iPSC lines, iMNs, add perturbations | TBD |  |  | 2 |  | 3 |  | 12 |  |  |  |  | Y1 Q4
Data Release 3
Imaging: Cell death assay and perturbations | iMN toxicity as determined by RM |  |  | 6 | 2 |  | 2 |  | 12 | 3 |  |  |  |  | Y2 Q1
| iMN glutamate toxicity- Excitotoxicity | 1 | 5 | 4 | 2 |  | 2 |  | 12 | 2 |  |  |  |  | Y2 Q1
| iMN Tunicamycin Toxicity: ER Stress | 1 | 6 | 1 | 2 |  | 2 |  | 12 | 2 | 1 |  |  |  | Y2 Q1
Transcriptomics | RNAseq for control and diseased iPSC lines, diseased iMNs, with perturbations | TBD |  |  | 2 |  |  |  | 12 | [5 empty] | Y2 Q1
Quantitative discovery proteomics (SWATH) | Based on SWATH library, compare iPSC and mature differentitated neurons, phosphorylation state, and add perturbations | 2 |  |  | 2 |  |  |  | 12,12* | [5 empty] | Y2Q1
Epigenomics | ATAC-Seq for control and disease iPSC lines, iMNs, add perturbations | TBD |  |  | 2 |  | 3 |  | 12 | [5 empty] | Y2 Q1
In your attached word document, it details 16 iPS lines. In this spreadsheet you describe 12, and its not clear which line doesn't appear here