## HMS-Proposed Milestones Dec2014
Proposed NeuroLINCS Dataset Milestones for September 2014-December 2015 (submitted 12-23-14)
Note 1: See attached document for NeuroLINCS QA/QC information and description of validation assays.
Note 2: All NeuroLINCS data will be released in formats compliant with LINCS metadata standards.
change to phenotypes
Datasets | Assay information | Cells | Perturbations |  |  | Timepoints | Targets/Readouts monitored | Data--estimated release dates |  |  | Comments/relevant urls (for released datasets)
|  | cell lines |  | small molecules | small molecule doses | timepoints (hours)
iMN toxicity as determined by RM | Imaging assay--monitoring cell survival in control, ALS, and SMA iMNs. iMNs will be transfected with a fluorescence reporter and imaged daily for 10 days. Images will be run through a custom analysis software package that tracks individual cells over time. The time of death (if it occurs) for each neuron will be determined. Neurite arborization will be determined using custom software analysis on these images. . | CS00iCTR-n2 |  |  |  | ~24 hours | cell fluorescence | Y1 Q3 | Y1 Q4 | Y2 Q1
|  | CS14iCTR-n6 |  |  |  | ~48 hours | survival time | Y1 Q3 | Y1 Q4 | Y2 Q1
|  | CS83iCTR-33n1 |  |  |  | ~72 hours | morphology | Y1 Q3 | Y1 Q4 | Y2 Q1
|  | CS25iCTR-18n2 |  |  |  | ~96 hours
|  | CS28iALS-n2A |  |  |  | ~120 hours
|  | CS29iALS-n1N |  |  |  | ~144 hours
CS30iALS-n1A
CS52iALS-n6A
CS32iSMA-n3
CS13iSMA-n1
83iSMA-n5
CS77iSMA-n5
|  | cell lines |  | small molecules | small molecule doses μM | timepoints (hours)
iMN glutamate toxicity- Excitotoxicity | iPSN Sensitivity to Glutamate-induced Toxicity To test iPSN sensitivity to glutamate-induced excitotoxicity, control and ALS/SMA iPSNs will be treated with various concentrations of L-glutamate (1, 3, 10, 30, 100 μM) for 2 – 8 hr in NDM, all concentrations for each experiment will be performed in triplicate. At the appropriate time point, cells will be incubated with 1 μM propidium iodide and 1 μM calcein AM for 30 min to visualize dead and live cells, respectively. Five to ten fields of view will then be imaged for each treatment using excitation/emission filters of 535/617 nm and 495/515 nm for propidium iodide and calcein AM, respectively. The number of propidium iodide positive and calcein AM iPSNs will be quantified using Image J over 3 separate experiments. | CS00iCTR-n2 |  | Glutamate | 1 | 2 hours | cell fluoresence after propidium iodide | Y1 Q3 | Y1 Q4 | Y2 Q1
|  | CS14iCTR-n6 |  |  | 3 | 4 hours | # cells with PI uptake | Y1 Q3 | Y1 Q4 | Y2 Q1
|  | CS83iCTR-33n1 |  |  | 10 | 6 hours |  | Y1 Q3 | Y1 Q4 | Y2 Q1
|  | CS25iCTR-18n2 |  |  | 30 | 8 hours
|  | CS28iALS-n2A |  |  | 100
CS29iALS-n1N
CS30iALS-n1A
CS52iALS-n6A
CS32iSMA-n3
CS13iSMA-n1
83iSMA-n5
CS77iSMA-n5
|  | cell lines |  | small molecules | small molecule doses μM | timepoints (hours)
iMN Tunicamycin Toxicity: ER Stress | Sensitivity to tunicamycin/ER Stress. iPS neurons will be differentiated in 24 well plates for 39 days before treatment with increasing tunicamycin concentrations (0, 0.1, 0.3, 0.6, 1.0, or 3.0 μM). After 24 h of incubation with tunicamycin, 0.5 μM of propidium iodide (PI) will be added to each well and incubated for 30 minutes. The PI signal will be imaged. For each treatment and dose, ≥ 10 images were taken per experiment, and the number of iPS neurons exhibiting PI uptake will be quantified using the “analyze particle” function of the Image J software (NIH). | CS00iCTR-n2 |  | tunicamycin | 0 | 24 hours | cell fluoresence after propidium iodide | Y1 Q3 | Y1 Q4 | Y2 Q1
|  | CS14iCTR-n6 |  |  | 0.1 |  | # cel with PI uptake | Y1 Q3 | Y1 Q4 | Y2 Q1
|  | CS83iCTR-33n1 |  |  | 0.3 |  | 10 images per experiment | Y1 Q3 | Y1 Q4 | Y2 Q1
|  | CS25iCTR-18n2 |  |  | 0.6 |  | “analyze particle” function of the Image J software | Y1 Q3 | Y1 Q4 | Y2 Q1
|  | CS28iALS-n2A |  |  | 1
|  | CS29iALS-n1N |  |  | 3
|  | CS30iALS-n1A |  |  |  |  | ex. 1 target, 1 phenotype
CS52iALS-n6A
CS32iSMA-n3
CS13iSMA-n1
83iSMA-n5
CS77iSMA-n5
Baseline RNAseq for control and diseased iPSC lines | Baseline gene expression dataset for QC and pipeline development -- 11 total control iPSC cell lines 3 in triplicate and 1 in duplicate and 28 diseased iPSC, 4 ALS and 4 SMA with replicates and with no additional perturbagen. Determine cell line variability and assay reproducibility. RNAseq QC statistics and expression correlation statistics will guide the development of QC statndards and appropriate analysis pipeline. | CS00iCTR-n2 |  | N/A |  |  | Read counts | Y1 Q3 | Y1 Q4 |  | FastQC, RSeqQC, RNA-SeQC, GENE-E, IGV
|  | CS14iCTR-n6 |  |  |  |  | FPKM | Y1 Q3 | Y1 Q4 |  | TuxedoSuite, DESeq, EdgeR
|  | CS83iCTR-33n1 |  |  |  |  | Statistically significant DEGs | Y1 Q3 | Y1 Q4
CS25iCTR-18n2
CS28iALS-n2A
CS29iALS-n1N
CS30iALS-n1A
CS52iALS-n6A
RNAseq for control and diseased iMNs | Baseline gene expression dataset for iMN and diseased state signature -- 4 control, 4 ALS, and 4 SMA iPSC-derived iMN with replicates and with no additional perturbagen. Generate gene expression signatures and analyze disease/control contrast for statistically significant differentially expressed genes. Generate disease signatures for future systems analysis: pathway, network, and category enrichment analysis, as well as for integration with other omics and machine learning analyses. | CS32iSMA-n3 |  | N/A |  |  | Read counts |  | Y1 Q4 | Y2 Q1 | QC and RNAseq analysis tools determined from baseline pilot study above.
|  | CS13iSMA-n1 |  |  |  |  | FPKM |  | Y1 Q4 | Y2 Q1
|  | 83iSMA-n5 |  |  |  |  | Statistically significant DEGs |  | Y1 Q4 | Y2 Q1
CS77iSMA-n5
RNAseq for control and diseased iMNs plus perturbations | Gene expression dataset for iMN and disease signature reponse to perturbagens -- 4 control, 4 ALS, and 4 SMA iPSC-derived iMN with replicates plus additional perturbagen. Generate gene expression signatures and for both disease and control and analyze perturb/disease & perturb/control contrasts for statistically significant differentially expressed genes. Using a GLM setup multi-factor design matrix to analyze disease vs control with each perturbagen as an additional factor. Generate signatures for future systems analysis: pathway, network, and category enrichment analysis, as well as for integration with other omics and machine learning analyses. | [5 empty] | Read counts |  |  | Y2 Q1 | QC and RNAseq analysis tools determined from baseline pilot study above.
|  |  |  | TBD |  |  | FPKM |  |  | Y2 Q1
[7 empty] | Statistically significant DEGs |  |  | Y2 Q1
QC and SOP development for proteomic analysis of iPSCs | a) MS analysis on the QE and Triple TOF MS instrument of trypsin digested iPSCs dervied from 4 control, 4 ALS and 4 SMA lines from 3 different wells and at multiple cell passages. | CS00iCTR-n2 | disease and control cell lines as iPSC |  |  |  | raw MS files (.raw .wiff) | Y1 Q3 | Y1 Q4 |  | http://www.ebi.ac.uk/pride/archive/
|  | CS14iCTR-n6 |  |  |  |  | Protein identifications and relative quantitation of proteins identified with FDR of 0.1%
CS83iCTR-33n1
CS25iCTR-18n2
CS28iALS-n2A
CS29iALS-n1N
CS30iALS-n1A
CS52iALS-n6A
CS32iSMA-n3
CS13iSMA-n1
83iSMA-n5
CS77iSMA-n5
SWATH global cellular protein quantification of iPSCs and motor neuron cultures | Build MS SWATH peptide library using the QE and 6600 MS instrument and use the library to identifiy and quantitate the proteome of individual control and disease cell lines. | CS00iCTR-n2 | disease and control |  |  |  | raw MS files (.raw .wiff) |  |  |  | http://www.ebi.ac.uk/pride/archive/
|  | CS14iCTR-n6 | iPSC and motor neuron |  |  |  | Protein identifications and relative quantitation of proteins identified with FDR of 0.1%
CS83iCTR-33n1
| A) build SWATH Library on iPSCs and motor neuron cell cultures | CS25iCTR-18n2 | [5 empty] | Y1 Q3 | Y1 Q4
| B) Run individual iPSC cells | CS28iALS-n2A | [6 empty] | Y1Q4
| C) Run individual mature motor neurons | CS29iALS-n1N | [6 empty] | Y1Q4
CS30iALS-n1A
CS52iALS-n6A
CS32iSMA-n3
CS13iSMA-n1
83iSMA-n5
CS77iSMA-n5
Phosphorylation state | Build MS SWATH data library: using the 6600 MS instrument analyzing either fractionated individuals and pools of iPSC dervied from 4 controls and SMA and ALS lines. | CS00iCTR-n2 | disease and control |  |  |  | raw MS files (.raw .wiff) |  |  |  | http://www.ebi.ac.uk/pride/archive/
|  | CS14iCTR-n6 | iPSC and motor neuron |  |  |  | Protein identifications and relative quantitation of phospho-peptides identified with FDR of 0.1%
CS83iCTR-33n1
| A) build SWATH Library | CS25iCTR-18n2 | [6 empty] | Y1Q4 | Y2 Q1
| B) Run individual iPSC cells | CS28iALS-n2A | [6 empty] | Y1Q4 | Y2 Q1
| C) Run individual mature motor neurons | CS29iALS-n1N | [6 empty] | Y1Q4 | Y2 Q1
CS30iALS-n1A
CS52iALS-n6A
CS32iSMA-n3
CS13iSMA-n1
83iSMA-n5
CS77iSMA-n5
Next stage with perturbations | SWATH analysis of proteomic changes in disease and control lines with various perturbations on iPSC and potentially neuron cultures. Analyze total protein and phosphorylation initially. | CS00iCTR-n2 | disease and control |  |  |  | raw MS files (.raw .wiff) |  |  |  | http://www.ebi.ac.uk/pride/archive/
|  | CS14iCTR-n6 | iPSC and motor neuron |  |  |  | Protein identifications and relative quantitation of proteins identified with FDR of 0.1%
CS83iCTR-33n1
| A) Run individual iPSC with stimulation A-N | CS25iCTR-18n2 | [7 empty] | Y2Q1
| B) Run individual mature motor neuron cultures with stimulation A-N | CS28iALS-n2A |  |  |  |  | Protein identifications and relative quantitation of phospho-peptides identified with FDR of 0.1% |  |  | Y2Q1
CS29iALS-n1N
| C) Run phospho-peptide enriched iPSC with stimulation A-N | CS30iALS-n1A | [7 empty] | Y2Q1
| D) Run phospho-peptide enriched motor neuron cultures with stimulation A-N | CS52iALS-n6A | [7 empty] | Y2Q1
CS32iSMA-n3
CS13iSMA-n1
83iSMA-n5
CS77iSMA-n5
Epigenomics |  | cell lines
General information and metadata links | Transposase-based epigenomic assay to map open chromatin regions and infer regulatory protein binding sites | CS00iCTR-n2
CS14iCTR-n6
CS83iCTR-33n1
CS25iCTR-18n2
CS28iALS-n2A
CS29iALS-n1N
CS30iALS-n1A
CS52iALS-n6A
CS32iSMA-n3
CS13iSMA-n1
83iSMA-n5
CS77iSMA-n5
ATAC-Seq Quality Control | Baseline ATAC-seq experiments for protocol assay optimization, QC and development of analysis methods -- 4 control, 4 ALS and 4 SMA iPSC cell lines with replicates, without additional perturbagens. Determine optimal conditions for purification of high quality nuclei to preserve chromatin structure and for transposase reaction (number of nuclei, enzyme concentration and incubation time) to avoid over- or under-digestion. Set up analysis pipelines, calculate signal-to-noise ratio and perform correlation and clustering tests to determine cell line variability and assay reproducibility between either technical or biological replicates and Identify potential problematic samples. |  |  | N/A |  |  | Raw Data (fastq) and BAM files (aligned reads) | Y1 Q3 |  |  | Bowtie, FastQC
[7 empty] | Genomic coordinates and intensity for each significant peak | Y1 Q3 |  |  | MACS, GPS
Baseline ATAC-Seq for control and disease iPSC lines | Baseline ATAC-seq experiments for protocol assay optimization, QC and development of analysis methods -- 4 control, 4 ALS and 4 SMA iPSC cell lines with replicates, without additional perturbagens. Annotate open chromatin regions and map transcription factor binding events in regulatory elements genome-wide. Generate chromatin accessibility signatures for each sample individually by calculating the enrichment of genomic regions relative to a set of control reads from Tn5-treated naked genomic DNA. Detect differential peaks between disease and control state. Generate disease signatures for future systems analysis and integration with other omics by 1) identifying genes mapping near differential peaks and detecting significantly enriched GO terms for these gene lists; 2) performing DNA foorprinting, motif scoring and applying regression methods to infer transcription factors responsible for gene expression signatures. |  |  | N/A |  |  | Raw Data (fastq) and BAM files (aligned reads) |  | Y1 Q4 | Y2 Q1 | Bowtie, FastQC
[7 empty] | Genomic coordinates and intensity for each significant peak |  | Y1 Q4 | Y2 Q1 | MACS, GPS
[7 empty] | Differentially expressed peaks relative to population control |  | Y1 Q4 | Y2 Q1 | MaNorm
ATAC-Seq for control and disease iMNs | Baseline ATAC-seq experiments for iMN and disease state signatures -- 4 control, 4 ALS, and 4 SMA iPSC-derived iMN lines with replicates without additional perturbagens. Annotate open chromatin regions and map transcription factor binding events in regulatory elements genome-wide. Generate chromatin accessibility signatures for each sample individually by calculating the enrichment of genomic regions relative to a set of control reads from Tn5-treated naked genomic DNA. Detect differential peaks between disease and control state. Generate disease signatures for future systems analysis and integration with other omics by 1) identifying genes mapping near differential peaks and detecting significantly enriched GO terms for these gene lists; 2) performing DNA foorprinting, motif scoring and applying regression methods to infer transcription factors responsible for gene expression signatures. |  |  | N/A |  |  | Raw Data (fastq) and BAM files (aligned reads) |  | Y1 Q4 | Y2 Q1 | QC and ATAC-Seq analysis tools determined from baseline pilot study above.
[7 empty] | Genomic coordinates and intensity for each significant peak |  | Y1 Q4 | Y2 Q1
[7 empty] | Differentially expressed peaks relative to population control |  | Y1 Q4 | Y2 Q1
ATAC-Seq for control and disease iMNs plus perturbations | ATAC-seq dataset for iMN and disease signature reponse to perturbagens -- 4 control, 4 ALS, and 4 SMA iPSC-derived iMN lines with replicates plus additional perturbagens. Generate chromatin accessibility signatures for each sample individually by calculating the enrichment of genomic regions relative to a set of control reads from Tn5-treated naked genomic DNA. Analyze perturb/disease & perturb/control datasets to detecte differentially enriched peaks reflecting changes in chromatin structures as a consequence of perturbation. Generate disease signatures for future systems analysis and integration with other omics and machine learning analyses. | [5 empty] | Raw Data (fastq) and BAM files (aligned reads) |  |  | Y2 Q1 | QC and ATAC-Seq analysis tools determined from baseline pilot study above.
|  |  |  | TBD |  |  | Genomic coordinates and intensity for each significant peak |  |  | Y2 Q1
[7 empty] | Differentially expressed peaks relative to population control |  |  | Y2 Q1

## Summary
*biological, microenvironment, small molecules
Data Release 1 |  | Data Generation | [10 empty] | Data release schedule
Project | Short Descriptive Label | perturbagens: external* |  |  | perturbagens: diseases | perturbagens: genetic | # bio reps | cell types |  | cellular phenotypes | targets/ readouts monitored | Total # of Measurements | Level 1 | Level 2 | Level 3 | Level 4
|  | count | doses | time points | count | count |  | cell lines | iPS, differentiated
Imaging: Cell death assay and perturbations | iMN toxicity as determined by RM |  |  | 6 | 2 |  | 4 |  | 12 | 3 |  |  | Y1 Q3
| iMN glutamate toxicity- Excitotoxicity | 1 | 5 | 4 | 2 |  | 4 |  | 12 | 2 |  |  | Y1 Q3
| iMN Tunicamycin Toxicity: ER Stress | 1 | 6 | 1 | 2 |  | 4 |  | 12 | 2 | 1 |  | Y1 Q3
Transcriptomics | RNAseq for control and diseased iPSC lines, diseased iMNs, with perturbations | TBD |  |  | 2 |  | 4 |  | 12 | 3 |  |  | Y1 Q3
Quantitative discovery proteomics (SWATH) | Based on SWATH library, compare iPSC and mature differentitated neurons, phosphorylation state, and add perturbations | 0 |  |  | 2 |  | 4 |  | 12 |  |  |  | Y1 Q3
Epigenomics | ATAC-Seq for control and disease iPSC lines, iMNs, add perturbations | TBD |  |  | 2 |  | 4 |  | 12 | 3 |  |  | Y1 Q3
Data Release 2
Imaging: Cell death assay and perturbations | iMN toxicity as determined by RM |  |  | 6 | 2 |  | 4 |  | 12 | 3 |  |  |  | Y1 Q4
| iMN glutamate toxicity- Excitotoxicity | 1 | 5 | 4 | 2 |  | 4 |  | 12 | 2 |  |  |  | Y1 Q4
| iMN Tunicamycin Toxicity: ER Stress | 1 | 6 | 1 | 2 |  | 4 |  | 12 | 2 | 1 |  |  | Y1 Q4
Transcriptomics | RNAseq for control and diseased iPSC lines, diseased iMNs, with perturbations | TBD |  |  | 2 |  | 4 |  | 12 | 3 |  |  |  | Y1 Q4
Quantitative discovery proteomics (SWATH) | Based on SWATH library, compare iPSC and mature differentitated neurons. | 0 |  |  | 2 |  | 4 |  | 12 |  |  |  |  | Y1 Q4
Epigenomics | ATAC-Seq for control and disease iPSC lines, iMNs, add perturbations | TBD |  |  | 2 |  | 4 |  | 12 | 3 |  |  |  | Y1 Q4
Data Release 3
Imaging: Cell death assay and perturbations | iMN toxicity as determined by RM |  |  | 6 | 2 |  | 4 |  | 12 | 3 |  |  |  |  | Y2 Q1
| iMN glutamate toxicity- Excitotoxicity | 1 | 5 | 4 | 2 |  | 4 |  | 12 | 2 |  |  |  |  | Y2 Q1
| iMN Tunicamycin Toxicity: ER Stress | 1 | 6 | 1 | 2 |  | 4 |  | 12 | 2 | 1 |  |  |  | Y2 Q1
Transcriptomics | RNAseq for control and diseased iPSC lines, diseased iMNs, with perturbations | TBD |  |  | 2 |  | 4 |  | 12 | 3 |  |  |  |  | Y2 Q1
Quantitative discovery proteomics (SWATH) | Based on SWATH library, compare iPSC and mature differentitated neurons, phosphorylation state, and add perturbations | 0 |  |  | 2 |  | 4 |  | 12 | [5 empty] | Y2Q1
Epigenomics | ATAC-Seq for control and disease iPSC lines, iMNs, add perturbations | TBD |  |  | 2 |  | 4 |  | 12 | 3 |  |  |  |  | Y2 Q1
In your attached word document, it details 16 iPS lines. In this spreadsheet you describe 12, and its not clear which line doesn't appear here